## ITC Contracting Fact Sheet

## Public contracting in Virginia is governed by the Virginia Public Procurement Act   (VPPA) http://www.eva.virginia.gov/buyers/pages/vppa.htm

## Many public entities (local governments etc) have their own Purchasing Policies that are based on the VPPA

## Competition is generally required, however Community Services Boards are exempt when purchasing services for the benefit of one individual; otherwise it is a bulk purchase and a competitive process should be competed

## There are multiple methods to contract:

## RFP – Request for proposals; a competitive process allowing many bidders the opportunity for competing for a contract award

## IPOS – Individual Purchase of service – when purchasing on behalf of an individual

## Sole Source – When there is no other entity that could provide the service; a non – competitive contract

## Fairfax Contracting Process  - RFPs

## How to get started - what services do you need that you can’t provide yourself?

## Requirements gathering – scope of services, tasks to be performed, deliverables, performance metrics...

## Writing and Revising – team works to create the RFP document

## SAC – Selection Committee of knowledgeable staff review the proposals, score, negotiate contracts and recommend contract awards.

## Monitoring and review – the most important aspect – need to continuously ensure serves performed according to contract and all outcomes are being met. Fairfax county example: performance based bonuses to providers

### Fairfax Infant & Toddler Connection Therapist Contracts on-line:

### http://www.fairfaxcounty.gov/CREGISTER/Default.aspx

### Search for “Early Intervention”

Sample RFP Timeline

| Task | Timeframe to Complete |
| --- | --- |
| Meet with all involved parties in the ITC program (Program Director, QA staff, therapists, financial contracts / procurement). Discuss what services you would like to contract for. | 30 days |
| Draft the RFP – this may take many iterations | 60 days |
| Following required Purchasing processes for advertising and issuing the RFP, as well as sending it directly to any providers you know of | Up to 30 days |
| Have a “pre-proposal conference” – a meeting with the potential bidders and ITC / contracting staff to answer all questions bidders may have. These will also be answered in writing and posted for all interested parties. | 14 days after RFP issuance |
| RFP Closes | 30-60 days after it is issued |
| ITC and contracting staff review the technical proposals, ask clarifying questions of bidders, review cost proposals and negotiate with bidders. May also include interviews of bidders. | 60-120 days after RFP closes |
| Award contract (s) and hold kick off meetings with contractors so all parties understand their responsibilities | 60-120 days after RFP closes |
| Monitor contract | Constantly |